## Workstations
Workstations
One row per place where work happens. A machine is not a separate line — it is what stands at the workstation. Capacity is the hours that workstation can absorb in one day. The four grey columns fill themselves in from the Schedule.
Code | Workstation | What stands there | Capacity (h/day) | Notes | Booked (h) | Peak day (h) | Days over | Utilisation (horizon)
WS-01 | Mill 1 | Haas VF-2, 3-axis | 8 | Service Fri PM
WS-02 | Mill 2 | DMG 5-axis | 8
WS-03 | Lathe | Okuma LB3000 | 8
WS-04 | Deburr bench | Manual, 2 operators | 16
WS-05 | Inspection | CMM | 8
WS-06 | Assembly bay | Floor area, 40 m² | 24 | Three jobs side by side

## Jobs
Jobs
One row per job. Pick the workstation from the dropdown — the grey columns look up its name and capacity, count the working days, and warn if a single job asks for more hours per day than the workstation has.
Job | Description | Workstation | Start | End | Hours/day | Workstation name | Capacity (h/day) | Working days | Total hours | Check
J-1041 | Bracket run, 250 off | WS-01 | 2026-08-10 | 2026-08-14 | 6
J-1042 | Housing, 40 off | WS-02 | 2026-08-10 | 2026-08-12 | 7
J-1043 | Shaft, 120 off | WS-03 | 2026-08-11 | 2026-08-18 | 5
J-1044 | Rush: repair fixture | WS-01 | 2026-08-12 | 2026-08-13 | 5
J-1045 | Housing, deburr | WS-04 | 2026-08-13 | 2026-08-17 | 8
J-1046 | First-article inspection | WS-05 | 2026-08-14 | 2026-08-14 | 4
J-1047 | Frame assembly | WS-06 | 2026-08-17 | 2026-08-26 | 16
Formulas:
Working days = IF(OR([Start]="",[End]=""),"",NETWORKDAYS([Start],[End]))

## Schedule
Schedule — booked hours per workstation per day
Entirely calculated — nothing to type here. Rows follow the Workstations sheet, so a workstation you add appears by itself. Red means booked beyond capacity; amber means exactly full, with nothing left for the rush job.
|  |  | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Sep | Oct | Oct
Code | Workstation | Cap | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02

## Read me
Orkyo capacity-planning template
A free, macro-free starting point for planning work onto the places it happens.
How to use it
1. Workstations — list every place where work happens. The machine standing at a workstation is part of it, not a separate row. Set the hours it can absorb in a day.
2. Jobs — one row per job. Pick the workstation from the dropdown, set the dates and the hours per day the job needs there.
3. Schedule — reads itself from the other two sheets. Red means booked beyond capacity; amber means exactly full.
Grey columns are calculated — do not type in them
• Jobs looks up the workstation's name and capacity (VLOOKUP), counts working days (NETWORKDAYS), totals the hours, and flags a job that asks for more per day than the workstation has.
• Workstations reports booked hours, the peak day, how many days are overbooked and utilisation across the horizon (INDEX/MATCH into the Schedule).
• Schedule takes its rows from Workstations, so a workstation you add appears here by itself, and every cell is a SUMIFS over Jobs.
Extending it
Room for 20 workstations and 200 jobs; the formulas are already there. To lengthen the horizon, copy the last date column of the Schedule to the right.
What this template cannot do
These limits are the spreadsheet's, not this file's:
• One editor. Whoever has the file has the plan; everyone else works from a copy that is already out of date.
• Hours only. It cannot see that the operator is on another job, that the fixture is in use, or that another site has room.
• No history. When a date moves, nothing records that it moved or why.
• Every change is manual. One rush job and the plan is rebuilt by hand.
Where the spreadsheet stops, and what the research says about trusting one:
https://orkyo.com/blog/outgrowing-the-machine-shop-excel-schedule/
Orkyo — production scheduling for jobs, workstations, people and tools.
https://orkyo.com
Free to use, copy and modify. No attribution required.